## Sheet1
Sprint 1
Objective | Name | Hours
Settng up MRS | Angel Montero, Li Jie Ye, Jialin Cao, Bin Lin | 12
Get familiar with MRS | Angel Montero, Li Jie Ye, Jialin Cao, Bin Lin | 6
MRS database analysis | Angel Montero, Li Jie Ye, Jialin Cao, Bin Lin | 6
Discussing project steps | Angel Montero, LiJie Ye, Jialin Cao, Bin Lin | 6
Sprint 2
Objective | Name | Hours
Connection between two clients on Desktop | Jialin Cao, Bin Lin | 16
Sending/receiving text between two clients on Desktop | Jialin Cao, Bin Lin | 8
Prototype using two gui on Desktop | Li Jie Ye | 6
Prototype debug | Li Jie Ye | 5
Prototype test | Angel Montero | 2
Android app UI design | Angel Montero | 5
Concepts discussion about how to implement to Anroid | Li Jie Ye, Bin Lin, Angel Montero, Jialin Cao | 5
Sprint 3
Objective | Name | Hours
Database Schema | Bin Lin | 10
Login/Register Servlet | Li Jie Ye | 18
Message Servlet | Jialin Cao | 15
Connecting database to servlet | Bin Lin | 8
Testing | Angel Montero | 3
Servlet debug | Li Jie Ye | 5
Revising database | Li Jie Ye | 7
Final test | Jialin Cao | 4
App UI discussion | Jialin Cao, Li Jie Ye, Bin Lin, Angel Montero | 5
Sprint 4
Objective | Name | Hours
Friendlist Servlet | Li Jie Ye | 14
Android app with login feature | Angel Montero | 18
Testing login feature | Jialin Cao | 3
Add sending message feature | Angel Montero | 21
Sending message feature test | Bin Lin | 2
Add receiving message feature | Angel Montero | 29
Receiving message feature test | Bin Lin | 5
Add display friendlist feature | Angel Montero | 26
Display friendlist feature test | Jialin Cao | 3
Revising database and servlet | Bin Lin, Jialin Cao | 2
Add user register feature | Angel Montero | 5
Add friend to friedlist feature | Angel Montero | 13
Testing register and add friend | Li Jie Ye | 5
Encryption | Angel Mntero | 40